## Skills Inventory
Skills
Skills | Team Member Names
Agile Project Management | Jared Dobry, Diane Ditko
User Story Creation | Jared Dobry, WeiLun Hsu, Diane Ditko
Requirements Decomposition | Jared Dobry, Hyun Jo Choi, Diane Ditko
Prototyping | Jared Dobry, WeiLun Hsu
Software Architecture Design | Jared Dobry, WeiLun Hsu, Diane Ditko
UI Design | Jared Dobry
Backend programming | Jared Dobry, Hyun Jo Choi
Frontend programming | Jared Dobry, Hyun Jo Choi
Software Testing | Jared Dobry, Hyun Jo Choi
Continuous Integration / Deployment | Jared Dobry
Verification/Validation | Hyun Jo Choi, Diane Ditko

## Roles and Responsibilities
Roles and Responsibilities
Role Title | Team Member Name (Primary, Backup) | Responsibilities
Project Manager | Hyunjo, Diane | Ensure cooperative environment, timely completion of tasks, maintain clear communication amongst group members, resolve conflicts regarding deliverables or schedule
UI lead | Jared | Coordinate the creation of personas, interaction and UI modeling, and prototypes.
Architecture lead | Diane | Coordinate the creation of the preliminary high level architecture diagrams and decisions including UML component diagrams, the package diagram, deployment diagram, state diagram, and views
Detailed Design lead | WeiLun Hsu | Ensure during requirements decomposition and detailed design that the team follows best practices using design patterns. Coordinate documentation of design decisions.
Implementation Lead | Jared | Assist in setup of development envrionments and the development of software components. Ensure implementation meets detailed design requirements.
Test Lead | Hyunjo | Discover defects in product, report to design and implementation lead with findings, produce successful operation of complete product

## Team Operating Procedures
Team Operating Procedures
How will the team communicate? | Slack, Email, Conferences in the Group 1 page in Canvas
How often? | During the week when necessary to discuss progress on goals outlined during meetings (at least once a week)
Meeting frequency and times? | Once per week 6:30 PM with additional meetings as needed. Tentatively on Friday/Saturday, but flexible for team members work schedules
How will the team collaborate? | Slack voice calls as well as utilizing real-time collaboration tools such as google drive and screen sharing
How are decisions made? | Team consensus (3/4 vote)
How are decisions documented? | Decisions will be documented on our GitHub wiki, found here: link
…

## Project Enviroment
Project Tools/Development Environment
Management/Collaboration/Communication Activity | Selected Tool(s)
Static Documentation | Git, GItHub Wiki
Collaborative Document Writing | Google Drive
Communication | Slack, Email
Project Management | Github Issues, Github Projects
Engineering Activity | Selected Tool(s)
Source Control | Git / GitHub
Diagram Creation | Lucidchart
Development | Visual Studio Code
Programming Language(s) | React (TypeScript), Electron
Testing (CI/CD) | GiHub Actions

## Effort Estimation and Tracking
Effort Estimation and Tracking
Effort (Person hours)
MAIN ACTIVITY | Sub-tasks | Jared Dobry |  | Hyun Choi |  | Wei-Lun Hsu |  | Diane Ditko |  | TOTAL ESTIMATED EFFORT per task or activity | TOTAL ACTUAL EFFORT per task or activity
|  | Estimated | Actual | Estimated | Actual | Estimated | Actual | Estimated | Actual
Requirements analysis
| 1.0 Use Case Definition (ALL) | 1 | 0.5 | 1 | 0.5 | 4 | 0.5 | 4 | 0.5 | 10 | 2
| 1.1 Context Model (D) | 1 |  | 1 |  | 3 |  | 4 | 2* | 9 | 0
| 1.2 Use Case Model (D) | 1 |  | 1 |  | 3 |  | 3 |  | 8 | 0
| 1.3 Functional Requirements Derivation (J) | 3 |  | 1 |  | 3 |  | 1 |  | 8 | 0
| 1.4 Document Use Case and Functional Requirements Matrix (J) | 2 |  | 1 |  | 3 |  | 1 |  | 7 | 0
| 1.5 Abuse Case Model (W) | 1 |  | 1 |  | 2 |  | 1 |  | 5 | 0
| 1.6 Identify Security Scenarios (W) | 1 |  | 1 |  | 1 |  | 1 |  | 4 | 0
| 1.7 Document Abuse Case and Security Scenario Matrix (J) | 2 |  | 1 |  | 2 |  | 1 |  | 6 | 0
| 1.8 Describe two most critical abuse cases (H) | 1 |  | 4 |  | 3 |  | 1 |  | 9 | 0
| 1.9 Non-functional Requirements Derivation (D) | 1 |  | 1 |  | 3 |  | 6 |  | 11 | 0
| 1.10 SEI description of three most priority quality scenarios (H) | 1 |  | 3 |  | 3 |  | 1 |  | 8 | 0
| 1.11 Document Compilation / Final Assignment Writing (ALL) | 4 |  | 4 |  | 4 |  | 4 |  | 16 | 0
Ux modeling | [9 empty] | 0 | 0
| Task 2.1 | [8 empty] | 0 | 0
| Task 2.2 | [8 empty] | 0 | 0
| Task 2.3 | [8 empty] | 0 | 0
Architecture design | [9 empty] | 0 | 0
| Task 3.1 | [8 empty] | 0 | 0
| Task 3.2 | [8 empty] | 0 | 0
| Task 3.3 | [8 empty] | 0 | 0
Detailed design | [9 empty] | 0 | 0
| Task 4.1 | [8 empty] | 0 | 0
| Task 4.2 | [8 empty] | 0 | 0
| Task 4.3 | [8 empty] | 0 | 0
Implementation
Task 5.1
Task 5.2
Task 5.3
Testing
Task 6.1
Task 6.2
Task 6.3
Project management
TOTAL ESTIMATED and ACTUAL EFFORT per student

## Risk Analysis and Management
Risk Analysis and Management
Risk description | Probability (Low=1, Medium=2, High=3) | Impact (Low=1, Medium=2, High=3) | Score (Probability x Impact) | Top 5 Priority Risks | Prevention or Mitigation actions
Technical Risk
Hosting the software for multiple users would require a server deployment | 3 | 1 | 3
Device Compatability (Desktop vs. Mobile) requires extra scope | 1 | 1 | 1
Application security | 2 | 1 | 2
Integration Issues |  |  | 0
Management Risk
Meeting time conflicts | 2 | 1 | 2
Inaccurate time estimations | 3 | 1 | 3
The scope of work isn't well defined yet | 3 | 2 | 6
Some tasks are dependent on others | 3 | 3 | 9
People Risk
Multiple members work full-time and may not have a lot of time to dedicate to the project | 3 | 3 | 9
Skill levels for each task vary between the group members | 2 | 1 | 2
Possible miscommuncation or forgetting to provide updates | 1 | 2 | 2
A team member is on travel mulitple times during the semester | 3 | 1 | 3
0

## Lessons Learned
Activity | What worked well and you would repeat in a future project? | What didn’t work well and what would you do differently about it in a future project?
Requirements Analysis |  | I'd like to have better UML modeling tools, and better requirements management tools. The free ones aren't great
UCD (Ux modeling)
Architecture design
Detailed design
Implementation
Testing
Project management